Status Report

Hivelet: A Web-Based Apartment Management System for Fe Galang Da Silva Boarding House

Week 3

28 September – 2 October 2026 (status as of 2 October 2026)

Manuscript

| Deliverable | Component | Status | Notes |
| --- | --- | --- | --- |
| Chapters 1–3 Manuscript | Corrections against the system as built: 33 units (not 32), PostgreSQL 17.6 on Supabase (not MySQL), Vue 3 + TypeScript and Express + TypeScript, GCash through Adyen, hosting on Vercel, technical evaluators added in §3.3 | Partial | Page-by-page fix list with paste-ready text written 26 Sep (FIXES_TO_CHAPTERS_1_TO_3.md); being applied to the manuscript. |
| Chapter 4 Manuscript | 4.1 Existing practices and system requirements | Partial | Complete except one cell in Table 5: how enquiries arrived before the system. Needs the owner's answer. |
| Chapter 4 Manuscript | 4.2 Development of the system (architecture and six modules) | Partial | Text complete and current with the system. Screenshots for Figures 4–8 still to be taken. |
| Chapter 4 Manuscript | 4.3 Pilot testing (Tables 8, 10, 11, 11A–11D) | Completed | Filled 1 Oct from the 30 Sep testing day, checked against the system's activity record. Tenant tasks: 31 of 34 attempts completed without help, none failed. |
| Chapter 4 Manuscript | 4.4 Evaluation based on ISO/IEC 25010 (Tables 12–22) | Pending | Survey with the IT evaluators on 3 Oct. Security evidence already in: A+ from Mozilla Observatory, SecurityHeaders and SSL Labs. |
| Chapter 4 Manuscript | 4.5 Deployment plan and strategies (Tables 24–25) | Partial | Stages 1–2 done (hosting; 937 income rows and 1,327 expense allocations transferred). Pilot use and hand-over in progress. |
| Chapter 5 Manuscript | Summary, conclusions and recommendations | Partial | Drafted and re-checked against Chapter 4. Final wording and the abstract follow the survey results. |
| Appendices | User manual (Appendix K), consent form, testing-day test cases and forms | Completed | Used on the 30 Sep testing day; manual updated 2 Oct. |

Status legend:    Completed    done and verified      Partial    under way      Pending    waiting on data or people

Prepared by: John Lloyd M. Cuario, Sean Jerve Ll. Rebancos, Victor Noel A. Napay, Kiel Hedrix V. Relos, Eljohn Paulo C. Loterte

Features

| System Feature | Description | Related Module | Status | Remarks |
| --- | --- | --- | --- | --- |
| Monthly Income ledger | The owner's income sheet in the same layout, grouped by cluster; income filed under the month the rent is for | Financial Tracking and Payment Recording | Completed | 937 historical income rows transferred from her workbook |
| Monthly Expenses ledger | Expenses split across property areas and categories, with totals | Financial Tracking and Payment Recording | Completed | 1,327 expense allocations transferred |
| Bills with rent and water | Rent and water kept separate; water = occupants × ₱200 (rate editable in settings); Linda units on a fixed amount and out of grand totals | Financial Tracking and Payment Recording | Completed | Water is computed, never typed (since 30 Sep). Garbage fee removed 30 Sep on the owner's instruction |
| Cash payment recording | Recorded with the owner's acknowledgement receipt; a repeated receipt is refused; a void is kept on record | Financial Tracking and Payment Recording | Completed | Testing day cases A-23 to A-25 passed |
| GCash online payment (Adyen) | Tenant pays through GCash; the payment waits in Pending Verification until the owner verifies it | Financial Tracking and Payment Recording | Completed | Live through the production webhook on Vercel; A-19 and T-14 passed |
| Excel downloads | Both ledgers export in the owner's format; choose one month, one year or everything | Financial Tracking and Payment Recording | Completed | Month/year/all choice added 2 Oct |
| Rent, month by month (tenant) | A sentence on how far payments reach, and 12 monthly bars: Paid, Due, Not entered, Not due yet | Tenant and Room Management | Completed | Only verified receipts count as paid |
| Room and rate directory | 33 units with cluster, floor, rate and status; every rate change recorded by a database trigger | Tenant and Room Management | Completed | A unit without a photo shows its floor plan (2 Oct) |
| Repair requests with photos | Tenant sends a request with priority and photo, follows it in a thread; only the owner closes it | Maintenance Ticketing and Notification | Completed | T-07 to T-09: 100% completed without help |
| In-app notifications | Alerts for payments, verifications, enquiries, comments and finished repairs; opens the record itself | Maintenance Ticketing and Notification | Completed | Pages refresh within about 2 seconds of a change by someone else |
| Public catalogue and enquiries | Live list of all 33 units; enquiry without an account; private link and reference code for the reply | Booking and Reservation Management | Completed | Never shows a tenant's name; public checks P-01 to P-08 passed (9 of 9) |
| Login ID and own password | Tenants sign in with an HV-##### login ID; own starting password, changed at first sign-in; owner can reset | Role-Based Access Control | Completed | Accounts reset 29 Sep; login IDs from 1 Oct |
| Audit trail | Every administrator action recorded; the database refuses edits or deletions | Role-Based Access Control | Completed | Activity screen removed 1 Oct on the adviser's advice; the trail stays in the database |
| Offline essentials and installable app | Installs from the browser; each person's last-loaded figures readable offline; writes stay online | Progressive Web Application | Completed | 13 of 14 screens opened offline on a production build |
| Dark mode and phone polish | Full dark mode, pull-to-refresh, filters on eight list screens, cards instead of tables on phones | All modules (interface) | Completed | Added 1–2 Oct |

Modules

| System Module | Purpose | Major Functions | Status | Remarks |
| --- | --- | --- | --- | --- |
| Role-Based Access Control | Control who can see and change what | Sign-in with login ID; forced password change; account lockout; permission on each of 55 routes; row-level security on all 22 operational tables; audit trail | Completed | Security headers A+; S-01 to S-12 passed |
| Tenant and Room Management | Keep the 33 units and their tenancies current | Unit registry (5 clusters, 3 floors); tenancies and occupants; onboarding; rate history; tenant password reset | Completed | 32 of 33 units occupied on live data |
| Booking and Reservation Management | Bring prospective tenants in through the public site | Public catalogue with live rates; unit enquiries; owner inbox and replies; enquiry converted to a tenancy | Completed | Reserved units stay visible but take no enquiries |
| Financial Tracking and Payment Recording | Replace the receipt book and workbook with one ledger | Bills (rent + water); cash recording with receipt guard; GCash through Adyen with owner verification; Monthly Income and Expenses; Excel export; Overview figures | Completed | 490 of 490 report reconciliations and 73 of 73 gateway checks passed |
| Maintenance Ticketing and Notification | Track repairs and keep everyone informed | Repair requests with photos and priority; threads; owner-logged repairs; in-app notifications | Completed | Tenants completed every repair task without help |
| Progressive Web Application | Make the system installable and usable on weak signal | Service worker and manifest; installable; offline read-only copy of essentials; connection notices | Completed | Opened on all ten addresses with no connection (Table 11A) |
| Evaluation and Hand-over (project activity) | Measure quality and turn the system over to the owner | ISO/IEC 25010 survey; training; user manual; full transition to the system as main record | Partial | Survey 3 Oct; manual handed over; training in progress |